## Scenarios
Registry artifact approval workflow - Scenarios
ID | Feature | Scenario Description | Prerequisites | Expected Result | Testers | Status | Scenario Type | Source Status | Depends On | Related Bug IDs | Needs Engineering Review | Notes
T-301 | Approval policy setup | Create an approved provider rule | Organization has usage control enabled and no provider approval rule exists | Can save the provider rule Rule is listed as approved on the approval policy page | Synthetic Admin Tester | ✅ Passed | UI | inferred |  |  | Yes | Synthetic scenario derived from provisional CUJ: Admin configures allowed registry artifacts.
T-302 | Run enforcement | Run a workspace using an unapproved provider | T-301 Workspace configuration references a provider that is not approved | Run fails before apply Error message identifies the unapproved provider | Synthetic Admin Tester, Synthetic Workspace Tester | ❌ Failed | Permissions | inferred | T-301 | BUG-001 | Yes | Synthetic scenario derived from provisional CUJ: Workspace run fails when an unapproved artifact is used.
T-303 | Run enforcement | Using Terraform CLI to create a blocked run | T-301 Local Terraform CLI is configured against the Workspace Under Test | Terraform CLI run returns an approval policy error Run is recorded as failed in the workspace run list | Synthetic CLI Tester | ⚪ Pending | CLI | inferred | T-301 |  | Yes | Synthetic CLI coverage for workspace operator path.
T-304 | Approval rule updates | Update an approved module rule after a failed run | T-302 A failed run exists for an unapproved module | Can add the module to approved artifacts Re-running the workspace completes without approval policy error | Synthetic Admin Tester | ✅ Passed | UI | inferred | T-302 |  | Yes | Synthetic scenario derived from provisional CUJ: Admin reviews and updates approval rules.
T-305 | Audit visibility | Check if approval decision is visible on the run details page | T-302 | Run details show blocked artifact name Admin can identify which approval rule is missing | Synthetic Admin Tester | ✅ Passed | UI | inferred | T-302 |  | Yes | Synthetic audience influenced expected result: admin must be able to diagnose missing approval.

## Bug_Tracker
Registry artifact approval workflow - Bug Tracker
Date Reported | Type | Feature | Scenario ID | Description | Severity | Owner | Evidence Links | Status | Release Blocking | Orphan Classification | Notes
2026-09-09 | Bug | Run enforcement | T-302 | T-302: Run fails but error message does not show the unapproved provider name | 2-High | Synthetic Engineering Owner | Synthetic run log: synthetic://run-log/T-302 | New | Yes | not-orphan | Synthetic linked bug for failed scenario.
2026-09-09 | Improvement | Audit visibility |  | No scenario. Admin audit table does not show who changed the approval rule | 4-Low |  | Synthetic screenshot: synthetic://screenshot/audit-table | New | No | no-scenario | Synthetic exploratory finding not tied to planned scenario.

## Summary
Registry artifact approval workflow - Release Readiness Summary
Summary Item | Value
Feature | Registry artifact approval workflow
Product Area | HCP Terraform Registry
QA Goal | bug-bash
Scenario Count | 5
Bug/Issue Count | 2
Validation Errors | 0
Validation Warnings | 1
Open Critical/High Bugs | BUG-001
Scenario Status by Feature
Approval policy setup | Pending: 0, In Progress: 0, Passed: 1, Failed: 0, Blocked: 0; Total: 1
Approval rule updates | Pending: 0, In Progress: 0, Passed: 1, Failed: 0, Blocked: 0; Total: 1
Audit visibility | Pending: 0, In Progress: 0, Passed: 1, Failed: 0, Blocked: 0; Total: 1
Run enforcement | Pending: 1, In Progress: 0, Passed: 0, Failed: 1, Blocked: 0; Total: 2
Bugs by Severity
2-High | 1
4-Low | 1
Bugs by Type
Bug | 1
Improvement | 1
Owner Workload
Synthetic Engineering Owner | 1

## Validation
Validation Warnings
Severity | Area | Row ID | Message
warning | Bug_Tracker | BUG-002 | Bug row has no linked scenario ID.